## Issues
106	<= max			Completed: 70%	8d 12:20			4d 03:50		70%

#	Added when	Type	Issue	Description	Est minutes	Priority	Milestone	Actual	Accuracy	Status	Comment
1	orig	Content	Check instructions	Check AEC re how to generate Australian coverage	20	Critical	1	4	-79%	Complete	Says to start with national and add WA, NSW and ACT. Assume national is made from other jurisdictions, so carry on as planned.
2	orig	Content	Clean up data	Remove spurious SA layers from feature services and reload	60	Critical	1	9	-86%	Complete	Check layers, checked on map: WA, ACT, SA, QLD, NT, VIC, TAS, NSW
3	orig	Style	Confirm colour	Choose a green as nice as the blue	10	Critical	1	16	+59%	Complete	Blue is navy: hsl(240 / Try “rainforest”: hsl(165, 100%, 25%) / #008060 / 50% transparent, so halve the lightness: / #004030 hsl(165, 100%, 12.5%)
4	orig	Style	Confirm thickness	Make border line thicker	20	Critical	1	5	-73%	Complete	5 pixel 50% transparent
5	orig	Style	Confirm scales	Confirm tile scales needed	20	Critical	1	14	-30%	Complete	Visibility from continent(1:50M) down to street (1:5K) / 1:9,028 yes / 1:4,514 no
6	orig	Style	Set max scale	Set max zoom on map in app	10	Critical	1	25	+155%	Complete	MapView.constraints.maxScale
7	orig	Content	Restyle layers	Restyle feature layers and save with new symbols and visibility	30	Critical	1	22	-27%	Complete
8	orig	Performance	Confirm performance	Confirm performance of basemap, layer WMS, and full load in app	60	Critical	1	83	+39%	Complete	Load map: OK (7.9s vs 6.4s for Google maps) / Redraw basemap: OK (2.1s vs 3.4s for Google maps) / Draw feature layer: FAIL (first 16s, redraw 18.5s) / Draw tile layer: OK (redraw 4.8s, min 3s)
11	orig	Content	Scrape tables	Scrape electorate/postcode tables	180	Critical	1	196	+9%	Complete	Cannot scrape from electorate search as many pages have multiple subpages accessible by JS functions. Write Python to scrape from postcode search instead. A few of these also have multi-pages but can be processed manually.
12	new	Code	Rework using tables	Rework app to avoid map for postcodes with only one electorate	480	Critical	1	122	-75%	Complete
13	orig	Code	Load app in background	Load map code in background while user types postcode	120	Critical	1	106	-12%	Complete	Loads only if needed
16	orig	Code	Add labels	Add labels for electorates (capitals, white on rainforest)	60	Critical	1	129	+115%	Complete
17	orig	Code	Query layer	query feature layers when click map	60	Critical	1	81	+35%	Complete
18	new	Content	Hand scraped pc	Manually extract data for 150 postcodes with more than one screen of localities and redo data processing to JSON	150	Critical	1	29	-81%	Complete
19	new	Code	Number pad	Add regex-restricted number pad to enter postcode on touch devices	180	Critical	1	350	+94%	Complete
20	orig	Code	Elec page	Style resulting electorate page and include links to 1. profile and and 3. find another electorate.	120	Critical	1	133	+11%	Complete
23	orig	Code	Refine design	Refine design appearance as needed	120	Critical	1	118	-1%	Complete
24	new	Design	Review design	Check that specs still describe what I want and revise if needed	45	Critical	1	113	+152%	Complete
25	new	Content	Geocode locs	Python script to geocode localities without electorates and write lat, long and zoom back to JSON.	180	Critical	1	107	-40%	Complete
26	new	Code	Group as other	For postcodes with multiple electorates, if locality list is long and mostly just one electorate, group those localities as “Other” to make the list much shorter.	240	Critical	1	130	-46%	Complete	Cut localities.json 87% from 1.4M to 175K!
27	new	Content	Fix HOLTZ	Fix Holtz where I tried adding a quote to add leading zero to postcode	45	Critical	1	88	+95%	Complete
29	new	Content	Multiple geocode results	Investigate multiple results from Warnings. Modify if needed.	60	Critical	1	108	+81%	Complete
31	new	Content	Sutho	Postcode 2232 returns only 3 locs. What about Sutherland or Grays Point for example?	120	Critical	1	34	-72%	Complete
32	new	Style	Flatten line symbol	Make layers opaque. Move transparency into code for easier control.	40	Critical	1	29	-27%	Complete	Done with addition of renderer
33	new	Style	Map background	Add background color to map. Also “loading map” gif	60	Critical	1	19	-68%	Complete	Used ocean colour to match outside of Australia-wide initial map
35	new	Code	No labels in ArcGIS for JS v4	Labeling coming soon for MapView(2D). Retreat from ArcGIS for JS v4.0 to v3.16.	120	Critical	1	48	-60%	Complete
36	new	Style	Refine home button	Button too obtrusive with solid fill home. Make outline instead and add hover bg colour for all buttons.	60	Critical	1	71	+18%	Complete
37	new	Content	2450 Coffs Harbour	Why does 2450 Coffs Harbour give a map?	10	Critical	1	8	-22%	Complete	From the Google maps extent, Coffs Harbour might extend a little way into Page.
38	new	Content	Deer Park	Why does Deer Park give a map?	10	Critical	1	24	+136%	Complete	It says Cunningham and Hughes. Likely an error. Msg'd Mark Da Silva 06/06/16 to confirm location. Also posted to FB. Mark confirmed location. So it's an error. Noted in Comments col of Localities sheet.
39	new	Content	Choice of one locality	Why does 3201 give a choice of one locality?	45	Critical	1	22	-50%	Complete
41	new	Code	Move text logic to showElec	Calls to showElec are messy. Clean them up by moving the heading text logic into the function.	20	Critical	1	27	+34%	Complete
42	new	Content	Sydney 2000	Sydney 2000 shouldn't need a map, it's in Sydney electorate!	30	Critical	1	68	+127%	Complete	Wrong data – see comments column of Localities sheet.
46	new	Code	Clean up XMLhttp	XMLhttp uses two almost identical functions	30	Critical	1	15	-50%	Complete
47	Wireframes 06.08	Code	Convert input to popup	Revise coding based on new Wireframes. Open map of Australia initially, and popup input screen over that.	90	Critical	1	13	-86%	Complete	Took longer than expected to get the workflow going again with map opening from start (initMap), and being reused, just changing extent and layer with each new call (drawMap). I had to understand where to place map and non-map functions in relation to each other in order to access the ESRI functions, how to create and reference the map inside these functions, and how to call the nested functions from the DOM.
48	Wireframes 06.08	Code	Add input buttons to map	Add buttons on map to reopen input screen.	60	Critical	1	125	+108%	Complete
49	Wireframes 06.08	Code	Convert elec to popup	Make elec page into a popup over the map.	60	Critical	1	11	-81%	Complete	Actually completed as part of 48, but assigned a nominal time of 10 minutes
52	Wireframes 06.08	Code	Add locate-me button	Add locate-me button.	60	Critical	1	120	+101%	Complete
59	Wireframes 06.08	Content	Extract cand data	Extract candidates data to spreadsheet and export to JSON	300	Critical	1	96	-68%	Complete
66	Wireframes 06.08	Code	Zoom to elec	Zoom map to electorate when popped-up	45	Critical	1	30	-32%	Complete
71	new	Code	Map bugs	Fix bugs with mapping. Set extent for elec when found via findPc or findLoc	60	Critical	1	21	-65%	Complete
72	new	Code	Input bugs	Create clearInput to fix invalid digit bug. Separate locOptions into a new function showLocs.	60	Critical	1	58	-4%	Complete
73	new	Code	Map Query bug	Won't draw lyr lines or respond to map click if Query is in require array. Won't zoom to elec if Query is NOT in require array.	300	Critical	1	113	-62%	Complete
77	new	Code	pcInput broken	From start can't enter postcode: textbox disappears whenever I press a numpad button, or when I enter a valid postcode.	90	Critical	1	95	+6%	Complete
86	new	Code	Fix sticky elec	Electorate stays at Cook – perhaps code is failing?	120	Critical	1	40	-67%	Complete
50	Wireframes 06.08	Code	Add elec search	Add electorate search	60	Important	1	60	%	Complete
51	Wireframes 06.08	Code	Add elec autocomplete	Add autocomplete to electorate search	60	Important	1	40	-33%	Complete
56	Wireframes 06.08	Code	Transition buttons to text boxes	Restyle input buttons to transition into text boxes	60	Important	1	5	-92%	Complete
57	Wireframes 06.08	Code	Remove Go button	Hide numpad and find postcode as soon as valid postcode entered	60	Important	1	40	-34%	Complete
58	Wireframes 06.08	Code	Hide numpad if desktop	On postcode button click, only show numpad if no previous mouse move detected	60	Important	1	41	-31%	Complete
65	Wireframes 06.08	Style	Add shadow	Add Modal shadow behind panels	45	Important	1	34	-23%	Complete
69	new	Content	Finalise candidates	Rescrape candidate data after editing finishes following nominations closing 10 June	60	Important	1	66	+10%	Complete
76	new	Code	Blank labels while zooming	See “undefined” while map is zooming out, until it redraws with correct elec labels. Also islands off Townsville (Herbert elec) show as undefined long after Herbert label shows correctly.	60	Important	1	31	-48%	Complete
82	new	Style	Make heading look distinctive		120	Important	1	76	-37%	Complete
85	new	Style	Colour major candidates	For the wow factor	120	Important	1	83	-31%	Complete
80	new	Style	Make Home return to initial state	Show input panel when home btn pressed	60	Useful	1	77	+29%	Complete
9	orig	Performance	Confirm platform	If layer WMS loads fast (<2s), but others too slow, try Google or OpenLayers instead	10	Critical	1			Dropped	Platform performance is OK (see #8 above)
10	orig	Business	Confirm credits	Confirm credits used and cost to buy more	20	Critical	1	7		Dropped	No need, as performance is OK without tiled layers. 42 credits remaining. / Used 7.05 for storage in last 14 days. / ACT Tile Service (took 2 minutes to prepare): do not have enough credits to perform this operation. / To purchase credits contact Esri Australia. / See this page for credit requirements.
14	orig	Content	Make tile layers	Create tile layers for all states	130	Critical	1			Dropped	No need, as performance is OK without tiled layers.
15	orig	Code	Use tile layers	Change layers to tile layers in app	30	Critical	1			Dropped	No need, as performance is OK without tiled layers.
28	new	Content	Sort geocode JSON attributes	For ease of reading (by me), give the loc properties a sensible order in the JSON output by geocode.py	60	Critical	1	34		Dropped
81	new	Code	Shows wrong elec	Geolocate, then select Barton by name. Zooms to Barton but shows Cook panel.	30	Critical	1	2		Dropped	Unable to replicate
61	Wireframes 06.08	Code	Add email-all	Add “email all” link to elec popup	120	Important	1			Dropped	Can't find all email addresses
62	Wireframes 06.08	Code	Add map link	Add “map” link to elec popup. Sets map extent to elec.extent and closes popup	45	Important	1			Dropped	Already sets map extent when elec is popped up
22	orig	Content	Add candidates	Add candidate details and links	360	Critical	2	143	-60%	Complete	Completed under issue #69 (Finalise candidates)
44	new	Content	Acknowledge data sources	AEC, Wikipedia, APH in Credits popup	60	Critical	2	40	-33%	Complete
54	Wireframes 06.08	Code	Add about popup	Add credits link to popup	60	Critical	2	114	+91%	Complete
55	Wireframes 06.08	Code	Add feedback link	Add feedback link to email me	60	Critical	2	130	+117%	Complete
64	new	Code	Can't show Mcpherson	Should be McPherson. Test by using 4226 > MERRIMAC > click SE quadrant	30	Critical	2	16	-47%	Complete
67	new	Code	Firefox issues	Make it work on Firefox. elecInput does nothing unless you type in (correctly capitalised) full elec name. mapHeader is odd but OK. pcInput and elecInput placeholders are initially grey, so appeared disabled. Geocode doesn't zoom. Pc 4226 works OK but selLoc is behind pcInput. This may be why it appears to do nothing with 2227 (Gymea/Bay are short words).	180	Critical	2	47	-74%	Complete
70	new	Content	Cand photos	Add candidate photos for majors at least. Need remaining Libs, Nats, other blue parties	360	Critical	2	131	-63%	Complete	Add photos for Libs outside NSW & Vic, also for Nats, CLP, LNP etc. Check each state/territoy has three cand pics.
75	new	Content	Convert PNG images	Lib Vic are all PNG and will give 404	90	Critical	2	37	-59%	Complete
79	new	Code	Find state when geolocating	After geolocating, use coords to lookup state from ArcGIS world map so we can load the right layer.	180	Critical	2	10	-94%	Complete
88	Alpha 1	Code	No datalist support	elecInput fallback not working for iPhone (Lee says can type but it does nothing)	180	Critical	2	140	-22%	Complete
89	new	Code	Fix numpad	Numpad broken since moving event handlers from html to js	45	Critical	2	71	+58%	Complete
95	new	Business	Register domain	findmyelectorate.com. Vins says use namecheap.com	90	Critical	2	15	-83%	Complete
96	new	Business	Tune website	Add robots.txt, favicon.ico	30	Critical	2	30	+1%	Complete
97	Pre-launch	Test	Cross-browser testing	Chrome, IE, Edge, Firefox	60	Critical	2	40	-33%	Complete
98	X-browser testing	Code	pcInput broken in IE11, Edge, FF	Does nothing when pc entered. IE11 Dev console: / SCRIPT445: Object doesn't support this action / findelec.js (544,3): var event = new MouseEvent('mousedown'); / typeof MouseEvent: object / Cf Chrome: typeof MouseEvent: function / How to open select input on IE11?	240	Critical	2	286	+19%	Complete
99	X-browser testing	Domain	Move to https	Chrome won't geolocate on http. Get SSL certificate and redirect findmyelectorate.com to https://	180	Critical	2	120	-33%	Complete
101	new	Business	Go live and promote!	On Facebook and Twitter	120	Critical	2	86	-29%	Complete
45	new	Doco	Document data flow	Show how to refresh all data in app	60	Important	2	60	%	Complete	Done in findelec.odp
74	new	Content	Compress images	Some candidate images over a MB and many over 500KB. Compress. Also resize to 300 wide and crop to upper 300 high	180	Important	2	23	-87%	Complete
84	new	Code	Fix phone bugs	Test on Chrome/Android and fix bugs found	120	Important	2	155	+29%	Complete
92	Alpha 1	Code	Fix translateX -50%	May simply need to add CSS selector prefixes. Affects Vins' Opera and my Safari 5/Win.	90	Important	2	19	-79%	Complete	Tried prefixes as per http://shouldiprefix.com/#transforms but it made no difference on Safari 5/Win. And http://caniuse.com/#feat=transforms2d says Opera Mini is the only modern browser which does not implement it. Have asked Vins to retest. Vins reports it worked! And sent screenshot.
93	new	Content	Add links for Labor		60	Important	2	85	+42%	Complete
94	new	Content	Add links for all parties		45	Important	2	19	-58%	Complete
100	new	Business	Add Google Analytics		60	Important	2	17	-71%	Complete
83	new	Code	Document scrolls on phone	Document window is about 30px too wide and 50px too tall	120	Important	2			Dropped	Disappeared by itself
103	new	Code	Fix bug with O'Connor	O'Connor doesn't show in the datalist in Chrome. Shows as invalid in FF.	45	Critical	3	22	-51%	Complete
104	new	Business	Email to all Greens candidates	Customised email to all Greens candidates with Mailchimp, promoting their electoral screen.	60	Important	3	60	%	Complete
102	new	Code	Allow link to elec	Add query param “e” to URL when elecPanel open. Body onLoad: parse URL and showElec(e) if e.	300	Critical	3	111
30	new	Content	Check geocoding issues	Manually check warnings and errors from geocoding. See geocode_checking.ods	150	Critical	4	62		In progress
43	new	Content	Reprocess after cleaning errors	Rerun extraction & geocoding after fixing the errors identified See Comments column of Localities sheet.	120	Critical	4
105	Post-launch	Bug	Missing * for 2232	Only Audley, RNP and Deer Park showing for 2232. See Issue105.txt.	120	Critical	4	60	-50%	Complete
106	Post-launch	Bug	Audley no longer geocoded	Audley is 2233 in Google geocode now (still 2232 in Google search) / AusPost has no result for Audley, Deer Park or Royal National Park / Maybe delete localities like this? / i.e. delete localities with ERROR - postcode mismatch / See Issue105.txt	60	Important	4		#VALUE!	Complete
60	Wireframes 06.08	Code	Mark up cands	Mark up candidates data in elec popup	120	Important	5	53		In progress	Still to add email address
78	new	Code	Query returns no attributes	Query returns no attributes	300	Important	5	102		In progress	Downgraded to important because it is only needed to showElec directly from geolocate. Have worked around by zooming to elec then displaying “Click map for electorate details” which is arguably ok.
87	Alpha 1	Code	Hard to scroll candidates	Maybe disableMapNavigation	60	Critical	5	8			Scrolls OK in lower part of cand table
53	Wireframes 06.08	Code	Add social media links	Add social media share buttons.	60	Highly Important	5
40	new	Content	Extent issues with some elecs	Sydney zooms to Lord Howe. Lingiari zooms beyond NT and even beyond WA.	45	Important	5
90	new	Code	minZoom limit on lyr	Make lyr disappear when zoomed out to Australia	30	Important	5
91	new	Code	Add waiting GIFs	E.g. for geocoding, map can be slow to zoom.	180	Important	5
34	new	Code	Web optimizer	Optimise load time by loading an ESRI js script customised for my app. https://developers.arcgis.com/javascript/3/jshelp/inside_web_optimizer.html	180	Important	10
68	new	Content	Senate	What about the Senate? Link from electorate to Senate candidates for seat?	300	Useful	10
21	orig	Code	Add live tally	Add link to tallyroom for election, even current data from API.	1440	Useful	20
63	new	Code	Frame external links	Frame external links into popup, with ← back icon at top left to return.	360	Useful	20

## Effort
Issue #	Issue	Date	Start	Finish	Elapsed	Issue total	Status	Notes
2	Clean up data		11:01:26	11:10:05	9	34	Complete
1	Check instructions		11:26:10	11:30:23	4	4	Complete
2	Clean up data		11:33:23	12:14:55	26	34	Complete
3	Confirm colour		11:58:00	12:13:53	16	16	Complete
4	Confirm thickness		12:17:09	12:22:28	5	5	Complete
5	Confirm scales		12:22:28	12:36:33	14	14	Complete
6	Set max scale		12:36:33	13:02:00	25	25	Complete
7	Restyle layers		13:02:00	13:23:55	22	22	Complete
8	Confirm performance		13:23:55	14:47:24	83	83	Complete
10	Confirm credits		14:47:24	14:54:34	7	7	Dropped
11	Scrape tables		09:24:46	12:40:55	196	366	Complete
11	Scrape tables		13:16:53	14:35:29	79	366	Complete	Excel code to scrape postcode files
11	Scrape tables		14:45:00	15:05:00	20	366	Complete	Python to parse postcode files
11	Scrape tables		19:15:00	20:25:55	71	366	Complete	Finish python to parse postcode files
12	Rework using tables		09:10:41	11:12:34	122	395	Complete	Use pivot tables to confirm approach: postcode, locality, map
12	Rework using tables		11:18:00	12:44:08	86	395	Complete	Design code and confirm approach with spreadsheet
12	Rework using tables		14:52:43	15:35:00	42	395	Complete	Redesign JSON to just answer the questions
12	Rework using tables		16:00:33	17:10:00	69	395	Complete	Start coding: read JSON, read user postcode input, search for postcode and respond differently for various cases
12	Rework using tables		19:00:27	20:16:05	76	395	Complete	Coding: add working elements for input, electorate display and locality selection
13	Load app in background		08:00:00	09:45:52	106	106	Complete
24	Review design		10:01:16	11:54:29	113	113	Complete	Revise wireframes
23	Refine design		11:54:58	13:53:13	118	429	Complete	Apply revised wireframes design
18	Hand scraped pc		17:46:04	18:15:00	29	154	Complete	Show Sarah how
19	Number pad		08:00:00	13:50:00	350	953	Complete
19	Number pad		15:45:00	17:50:00	125	953	Complete
19	Number pad		19:10:00	20:25:00	75	953	Complete
19	Number pad		09:00:00	13:00:00	240	953	Complete
19	Number pad		15:00:00	16:25:00	85	953	Complete
19	Number pad		19:12:00	20:30:00	78	953	Complete
25	Geocode locs		06:15:00	08:02:14	107	517	Complete
25	Geocode locs		08:57:22	09:30:00	33	517	Complete	At Stewart Toyota
25	Geocode locs		09:45:00	13:35:00	230	517	Complete
25	Geocode locs		16:30:00	18:15:00	105	517	Complete
18	Hand scraped pc		19:15:00	21:20:00	125	154	Complete
27	Fix HOLTZ		08:42:27	10:10:00	88	88	Complete
26	Group as other		10:35:00	12:45:00	130	130	Complete
25	Geocode locs		13:18:16	14:00:00	42	517	Complete
28	Sort geocode JSON attributes		14:00:00	14:33:50	34	34	Dropped
29	Multiple geocode results		16:36:47	18:25:16	108	108	Complete	Refined geocoder to pick the best result or warn if none
30	Check geocoding issues		19:15:00	20:16:53	62	346	In progress
31	Sutho		08:05:19	08:38:54	34	34	Complete
32	Flatten line symbol		08:39:46	09:09:00	29	29	Complete	Done with addition of renderer
16	Add labels		09:09:00	11:17:52	129	129	Complete	Stymied because need to retreat from ArcGIS for JS v4.0 to v3.16
35	No labels in ArcGIS for JS v4		10:30:00	11:17:52	48	103	Complete
35	No labels in ArcGIS for JS v4		13:51:11	14:46:08	55	103	Complete
36	Refine home button		14:46:08	15:57:09	71	71	Complete
33	Map background		15:57:09	16:16:38	19	19	Complete
17	Query layer		16:40:26	18:01:33	81	203	Complete
17	Query layer		19:11:48	21:13:38	122	203	Complete
39	Choice of one locality		15:05:31	15:27:53	22	60	Complete
39	Choice of one locality		16:09:02	16:40:00	31	60	Complete
41	Move text logic to showElec		16:40:00	17:06:49	27	27	Complete
39	Choice of one locality		19:13:04	19:19:46	7	60	Complete
37	2450 Coffs Harbour		19:25:00	19:32:50	8	8	Complete
38	Deer Park		19:32:50	19:56:26	24	24	Complete
42	Sydney 2000		19:56:26	21:04:24	68	68	Complete
20	Elec page		08:04:56	10:18:21	133	425	Complete	Load electorate details from JSON file, add link to electorate profiles
46	Clean up XMLhttp		10:18:28	10:33:36	15	15	Complete
20	Elec page		10:34:09	11:05:58	32	425	Complete	Show showElec from map as well as from inputPc
30	Check geocoding issues		11:06:24	13:30:00	144	346	In progress	Train Sarah
20	Elec page		15:02:41	15:21:54	19	425	Complete	Show showElec from map as well as from inputPc
30	Check geocoding issues		15:21:58	16:30:00	68	346	In progress	Train Sarah
30	Check geocoding issues		07:40:00	08:52:17	72	346	In progress	Do the next few
20	Elec page		08:52:24	09:47:56	56	425	Complete	Get electorate name from click on map
20	Elec page		10:10:00	11:16:36	67	425	Complete	Get electorate name from click on map
20	Elec page		11:16:44	13:15:00	118	425	Complete	Style elec div
23	Refine design		16:00:00	18:10:29	130	429	Complete	Integrate screens in Wireframe into flexible app supporting multiple workflows
23	Refine design		20:00:00	23:00:00	180	429	Complete	Refine Wireframe
47	Convert input to popup		16:17:02	16:30:00	13	244	Complete
47	Convert input to popup		17:20:01	17:45:00	25	244	Complete
47	Convert input to popup		19:13:27	21:16:48	123	244	Complete
47	Convert input to popup		21:40:00	23:02:17	82	244	Complete
48	Add input buttons to map		08:22:15	10:27:17	125	213	Complete	Also added transition to visually link input panel to map buttons
65	Add shadow		10:27:17	11:01:46	34	34	Complete
48	Add input buttons to map		11:01:46	12:30:00	88	213	Complete	Fix complete workflow
49	Convert elec to popup		12:30:00	12:41:20	11	11	Complete
66	Zoom to elec		12:41:20	13:11:45	30	206	Complete
59	Extract cand data		19:45:08	21:21:22	96	215	Complete	From Wikipedia to Candidates spreadsheet Source, then from there to Candidates normalised ready for JSON
59	Extract cand data		07:48:56	09:48:00	119	215	Complete
60	Mark up cands		09:48:00	10:40:41	53	128	In progress
66	Zoom to elec		11:44:49	13:20:00	95	206	Complete	Only working on map click: make it work from findPc and findLoc
66	Zoom to elec		14:08:34	14:56:47	48	206	Complete	Zooms OK but won't draw lyr lines or respond to map click if Query is in require array
66	Zoom to elec		18:51:02	19:22:44	32	206	Complete	Stuck
70	Cand photos		19:22:44	21:34:09	131	957	Complete	Downloaded Greens NSW photos and started matching to electorates by filename.
70	Cand photos		08:54:29	11:22:43	148	957	Complete	Clean photo file names for Greens
70	Cand photos		11:58:34	12:37:57	39	957	Complete	Clean photo file names for Greens SA, Vic & WA
70	Cand photos		12:38:06	13:09:26	31	957	Complete	Code in photos or blank if missing
60	Mark up cands		14:13:53	15:00:00	46	128	In progress	Sort by major parties first then name
60	Mark up cands		20:15:45	20:45:00	29	128	In progress	Sort by major parties first then name
71	Map bugs		10:00:52	10:22:00	21	30	Complete	Fix bug on map extent via findPc and findLoc
72			10:22:00	11:19:36	58	58	Complete
71	Map bugs		11:19:36	11:28:44	9	30	Complete	Investigatedbug on click map to show elec. This is the Query bug. Added issue (73).
70	Cand photos		11:29:04	14:17:08	168	957	Complete	Extract Labor candidate photos
22	Add candidates		15:56:34	18:20:00	143	424	Complete	Candidate and party links: Liberal NSW
22	Add candidates		18:50:00	19:11:48	22	424	Complete	Liberal VIC
22	Add candidates		19:41:12	20:45:04	64	424	Complete	Create JSON for candidate and party links
22	Add candidates		14:13:31	16:37:20	144	424	Complete	Code in candidate and party links
22	Add candidates		19:42:54	20:34:16	51	424	Complete	Wrestle with Candidates.ods trying to get CandLinks col B to work for all rows. Then created Candidates_2 to get towards a sheet with one candidate per row. (Can create this in Brackets with Split and Remove empty lines). But stopped by faulty formulas – see pink cells ir R5:S5. Completed under Issue #69 (Finalise candidates).
69	Finalise candidates	15-Jun-16	07:42:41	08:48:55	66	314	Complete	New candididates from AEC
69	Finalise candidates	15-Jun-16	18:00:00	18:30:00	30	314	Complete	New candididates from AEC
69	Finalise candidates	16-Jun-16	20:00:00	23:38:00	218	314	Complete	New candididates from AEC
70	Cand photos	17-Jun-16	07:45:00	09:00:30	76	957	Complete	Rename and move Lib photos (Vic & NSW only)
58	Hide numpad if desktop	18-Jun-16	18:22:02	19:03:17	41	327	Complete	Also add elec & locate buttons and transition from button to input
58	Hide numpad if desktop	18-Jun-16	19:50:00	21:15:34	86	327	Complete
50	Add elec search	19-Jun-16	11:30:00	12:30:00	60	60	Complete
57	Remove Go button	19-Jun-16	12:30:00	13:09:50	40	40	Complete
58	Hide numpad if desktop	19-Jun-16	15:07:57	18:20:23	192	327	Complete
58	Hide numpad if desktop	19-Jun-16	18:39:52	18:47:07	7	327	Complete
56	Transition buttons to text boxes	19-Jun-16	18:47:07	18:52:04	5	5	Complete
51	Add elec autocomplete	19-Jun-16	10:50:00	11:30:00	40	40	Complete
52	Add locate-me button	19-Jun-16	18:52:04	20:52:29	120	243	Complete
73	Map Query bug	20-Jun-16	09:52:50	11:46:15	113	113	Complete	Add state to candidates.json so we can draw and select from the right layer after finding by elec name. / Now it works! Zooms to electorate. And then it zooms to Postcode as well. Still draws elec lines and labels. Still zooms to elec when map clicked. / Perhaps the workflow for findElec does something critical which was missing from the workflow for findPc. If so, it will fail to zoom when findPc is run first.
52	Add locate-me button	20-Jun-16	11:52:44	13:55:27	123	243	Complete	Zoom straight to elec, don't prompt to click map. / Zooms OK but can't get elec name from event attributes in order to showElec
78	Query returns no attributes	20-Jun-16	14:47:47	16:30:00	102	174	In progress	Testing to address missing attributes bug
78	Query returns no attributes	20-Jun-16	19:39:35	20:51:23	72	174	In progress	testQuery works to find and name elec by: / * map click / * point (coords) / * geolocation / * elec name
77	pcInput broken	21-Jun-16	10:23:59	11:59:13	95	95	Complete	Fixed!
81	Shows wrong elec	21-Jun-16	12:07:46	12:10:09	2	2	Dropped	Unable to replicate
82	Make heading look distinctive	21-Jun-16	12:10:09	13:25:42	76	76	Complete
80	Make Home return to initial state	21-Jun-16	13:25:42	14:43:08	77	77	Complete
84	Fix phone bugs	21-Jun-16	16:10:00	18:45:00	155	569	Complete	Stymied on making candidates occupy remaining height in panel
84	Fix phone bugs	21-Jun-16	21:00:14	03:21:34	381	569	Complete
85	Colour major candidates	22-Jun-16	10:27:05	11:50:00	83	92	Complete
85	Colour major candidates	22-Jun-16	12:32:26	12:41:11	9	92	Complete
86	Fix sticky elec	22-Jun-16	16:02:59	16:42:55	40	40	Complete	Only shows one candidate
76	Blank labels while zooming	22-Jun-16	16:44:32	17:15:27	31	31	Complete	Worked around by turning off labels during map-update and map-zoom, and turming on again and redrawing 100 ms after update-end or zoom-end.
84	Fix phone bugs	22-Jun-16	19:37:09	20:10:00	33	569	Complete	Blur inputs and close button in closePanel
75	Convert PNG images	22-Jun-16	20:10:00	20:47:02	37	37	Complete	Allow png as fall-back image
87	Hard to scroll candidates	23-Jun-16	09:16:56	09:25:00	8	8	0	Told map to disable navigation but it doesn't help
88	No datalist support	23-Jun-16	12:00:00	14:20:00	140	302	Complete	Tried a supplied polyfiller but had trouble with positioning, clicking scrollbar making it disappear, and it didn't fire showElec
89	Fix numpad	27-Jun-16	09:53:32	11:04:28	71	71	Complete	Fixed but took a while to figure out how (not to have) to pass parameters to the event at create time
88	No datalist support	27-Jun-16	11:04:28	13:46:18	162	302	Complete	Fixed on iPhone 6 (iOS 9 Shiny) according to Lee. Offers drop-down when one letter typed. When elec selected from dropdown, shows candidates and zooms to electorate.
45	Document data flow	23-Jun-16	11:30:00	12:30:00	60	60	Complete	Diagrammed data flow in presentation findelec.odp. Estimated time.
64	Can't show Mcpherson	27-Jun-16	14:22:21	14:38:18	16	16	Complete	Fixed by proper-naming the elec name found in the boundary set
79	Find state when geolocating	27-Jun-16	14:45:00	14:55:00	10	160	Complete
79	Find state when geolocating	27-Jun-16	15:11:45	15:26:28	15	160	Complete
79	Find state when geolocating	27-Jun-16	16:35:13	17:27:52	53	160	Complete
79	Find state when geolocating	27-Jun-16	18:53:15	20:16:00	83	160	Complete	Hide popup
92	Fix translateX -50%	27-Jun-16	20:20:00	20:39:12	19	19	Complete	Tried prefixes as per http://shouldiprefix.com/#transforms but it made no difference on Safari 5/Win. And http://caniuse.com/#feat=transforms2d says Opera Mini is the only modern browser which does not implement it. Have asked Vins to retest. Vins reports it worked! And sent screenshot.
70	Cand photos	28-Jun-16	09:07:34	13:18:23	251	957	Complete	Got cand photos and links for remaining Libs. Only Nats (photos/links) and Labor (links) to go.
70	Cand photos	28-Jun-16	14:38:36	16:09:53	91	957	Complete	Nats photos and links
70	Cand photos	28-Jun-16	16:10:01	16:30:53	21	957	Complete	Rename lib qld images to _lnp_ / Rename lib nt images to _clp_
93	Add links for Labor	28-Jun-16	19:34:54	21:00:00	85	85	Complete
94	Add links for all parties	28-Jun-16	21:00:00	21:18:42	19	42	Complete
95	Register domain	28-Jun-16	21:18:42	21:33:45	15	15	Complete
94	Add links for all parties	29-Jun-16	07:46:21	08:09:54	24	42	Complete	Fix bug which showed up with party links and broke elecPanel
54	Add about popup	29-Jun-16	08:15:34	10:10:00	114	114	Complete
96	Tune website	29-Jun-16	13:00:00	13:30:25	30	30	Complete
44	Acknowledge data sources	29-Jun-16	10:10:00	10:50:01	40	40	Complete
55	Add feedback link	29-Jun-16	10:50:01	13:00:00	130	130	Complete
97	Cross-browser testing	29-Jun-16	14:45:00	15:25:00	40	191	Complete
97	Cross-browser testing	29-Jun-16	16:55:00	17:35:00	40	191	Complete
99	Move to https	29-Jun-16	19:30:00	21:30:00	120	120	Complete
98	pcInput broken in IE11, Edge, FF	30-Jun-16	06:53:36	11:40:00	286	286	Complete
100	Add Google Analytics	30-Jun-16	11:40:00	11:57:13	17	17	Complete
97	Cross-browser testing	30-Jun-16	13:00:00	14:38:00	98	191	Complete
97	Cross-browser testing	30-Jun-16	15:00:00	15:12:43	13	191	Complete
67	Firefox issues	30-Jun-16	12:12:51	13:00:00	47	47	Complete
101	Go live and promote!	30-Jun-16	15:18:16	16:43:59	86	86	Complete	Go live and test prod on browsers
74	Compress images	30-Jun-16	17:54:00	18:17:22	23	23	Complete
102	Allow link to elec	1-Jul-16	11:09:00	13:00:00	111	241	0
103	Fix bug with O'Connor	1-Jul-16	13:00:00	13:22:12	22	22	Complete	O'Connor didn't show in datalist because it didn't match the pattern. When I fixed that, I then needed to escape the apostrophe before using it in the SQL where clause.
102	Allow link to elec	1-Jul-16	16:20:00	18:30:00	130	241	0
104	Email to all Greens candidates	1-Jul-16	19:00:00	20:00:00	60	60	Complete	Email to all Greens candidates
105	Missing * for 2232	2-Jul-16	16:00:00	17:00:00	60	60	Complete
106	Audley no longer geocoded	3-Jul-16	12:40:01				Complete
106	Audley no longer geocoded	3-Jul-16	18:46:31				Complete
106	Audley no longer geocoded	4-Jul-16	14:18:34	14:35:42	17	46	Complete	Move these localities to a LocalitiesDeleted sheet
106	Audley no longer geocoded	4-Jul-16	17:05:51	17:15:00	9	46	Complete
106	Audley no longer geocoded	4-Jul-16	17:21:00	17:27:19	6	46	Complete
106	Audley no longer geocoded	4-Jul-16	18:30:00	18:43:14	13	46	Complete

## Performance
Test #	Platform	What	Try 1	Try 2	Try 3	Try 4	Try 5	Min	Max	Average	Median	Range/Average	Test details
1	ArcGIS API for Javascript	Load map	8.5	7.79	7.97	7.3	7.74	7.3	8.5	7.9	7.8	8%	App reload to display basemap
2	ArcGIS API for Javascript	App reload to display electorates	14.5	15.94	18.85	16.31	14.3	14.3	18.9	16.0	15.9	18%	Ctrl-R to reload page
3	ArcGIS API for Javascript	Map redraw at postcode w/ electorates	11.74	17.46	23.07	21.15	19.25	11.7	23.1	18.5	19.3	37%	Having entered postcode in search, click on correct result.
4	Google maps	Load map	7.89	5.93	6.76	5.6	5.59	5.6	7.9	6.4	5.9	24%	Ctrl-click on map in Google search results for Gymea
5	Google maps	Map redraw at postcode	2.3	3.44	3	3.06	5.19	2.3	5.2	3.4	3.1	53%	Having entered postcode on Google map, click search
6	ArcGIS API for Javascript	Map redraw at postcode	1.86	2.18	1.56	2.9	1.8	1.6	2.9	2.1	1.9	41%	Commented out layer code. Having entered postcode in search, click on correct result.
7	ArcGIS API for Javascript	Map redraw at postcode w/ tileLayer	7.62	3.01	3.63	3.5	6.18	3.0	7.6	4.8	3.6	59%	Used World Dark Gray Base